## List1
Number | Description | Owner | Effect | Probability | Impact | Level of risk | Mitigate strategy | Cost of that strategy
1 | There will be a licence problem with content (like images, geodata) | Developer | Deleting that data, fee | 60% | Low | Medium | Avoid downloading data with unknown or not open licence | 15h
2 | Not getting contract with flight seller | Founder/Marketing | Low traffic | 25% | Medium | High | Set proper advertising, prepare good presentation for flight seller, try to integrate to their system | 100h
3 | Not representative images in the database, which leads to poor service | Developer | Low traffic | 20% | High | High | Manualy add images to database, train clasifier which can pick good images after training | 50h + 80h
4 | Bad development (code, design, testing) | PM/HR/Founder | Delay, bad quality, loosing customers | 30% | Very High | Very High | Using social network to hire someone or some agencies (toptal ...) | 10h
5 | DDOS attact | Developer | Bad loading of pages | 10% | Low | Low | Using defense against DDOS | 20h
6 | Bad UX/UI | Designer | Loosing customers because they get lost | 10% | Medium | More than Low | Using good practises, get feedback from customers | 15h
7 | ß
8
9
10
11
12
13
14
15
16